REWARDZ RISK REGISTER

# Risk Assessment Framework

| Likelihood | 1 = Unlikely; 2 = Possible; 3 = Probable |
| --- | --- |
| Impact | 1 = Low; 2 = Significant; 3 = Critical |
| Risk Rating | Likelihood × Impact: 1–2 = Low; 3–4 = Medium; 6 = High; 9 = Critical |

# 1. Regulatory & Legal Risks

| ID | Risk | L | I | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- |
| R01 | FCA SPI registration rejected or delayed, preventing legal fund handling. | 2 | 3 | 6 HIGH | Engage specialist FCA counsel at Day 0. Stripe Connect routing reduces principal fund-holding exposure significantly. Assess Small Payment Institution vs Registered Account Information Service Person pathway. |
| R02 | GDPR breach through inadequate data handling architecture. | 2 | 3 | 6 HIGH | Privacy-by-design: PII classification on all customer data nodes at architecture level. Data minimisation policy. DPO appointed or contracted before launch. |
| R03 | Merchant agreement inadequacy — terms unenforceable or ambiguous on pooled liability. | 2 | 2 | 4 MEDIUM | Standardised merchant agreement drafted by legal counsel. Covers: transaction fees, settlement terms, data usage, termination, early adopter lock-in mechanics. |
| R04 | Consumer credit / e-money regulation triggered by cash wallet model. | 2 | 2 | 4 MEDIUM | Legal opinion commissioned on cash wallet classification. 0.001p nominal cash value mechanism used by all major UK loyalty platforms as legal protection — assess applicability. |

# 2. Technology & Security Risks

| ID | Risk | L | I | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- |
| T01 | QR code replay attack — customer presents previously scanned code to earn unauthorised stamps. | 2 | 2 | 4 MEDIUM | Cryptographic QR cycling: 30-second HMAC-SHA256 time window + immediate post-scan server-side invalidation. Used token list maintained server-side. |
| T02 | BYOD merchant device loss — staff phone with authenticated merchant session falls into third-party hands. | 2 | 2 | 4 MEDIUM | Session timeout (15-minute inactivity); remote session revocation via admin panel; transaction velocity alerts on merchant account; biometric lock requirement for merchant app. |
| T03 | Customer app spoofing — customer device mounts fake merchant scan responses to earn stamps fraudulently. | 2 | 3 | 6 HIGH | All stamp earn events validated server-side against known merchant QR token state. Client app cannot self-grant stamps — all events are server-authorised. |
| T04 | Infrastructure outage — cloud provider downtime prevents merchant scanning. | 2 | 2 | 4 MEDIUM | Multi-availability-zone deployment; offline grace mode (stamps queued locally, synced on reconnect with server-side deduplication); SLA monitoring. |
| T05 | API key or credential compromise. | 1 | 3 | 3 MEDIUM | Secrets management (Kubernetes secrets / Vault); no credentials in source code; automated credential rotation; penetration testing pre-launch. |

# 3. Commercial & Market Risks

| ID | Risk | L | I | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- |
| C01 | Merchant cold-start failure — insufficient merchants to create network value at launch. | 2 | 3 | 6 HIGH | Minimum 20 committed merchants before consumer app launch. Founder-led acquisition. 90-day free period for founding cohort reduces adoption risk. |
| C02 | Consumer adoption below viable threshold. | 2 | 2 | 4 MEDIUM | Frictionless first-scan (browser deep-link, 30-second signup). Founder-led in-venue activation. Social proof campaign. Network effect value proposition ('earn everywhere'). |
| C03 | Well-capitalised competitor enters market within 6 months. | 2 | 3 | 6 HIGH | First-mover speed strategy. Early adopter lock-ins prevent displacement. Merchant installed base is sticky — switching has operational cost. Data advantage compounds with time. |
| C04 | Unit economics validation failure — model does not perform as projected. | 2 | 2 | 4 MEDIUM | Week 15 Go/No-Go gate based on research programme. Minimum viable economics defined pre-research. Pivot optionality maintained: platform architecture is vertical-agnostic. |
| C05 | International expansion failure (US/China) by Month 6 target. | 3 | 1 | 3 MEDIUM | International entry by Month 6 is aspiration with risk. Define minimum viable international presence — a signed partner agreement qualifies. Full operational entry may require Month 12+. |

# 4. Operational Risks

| ID | Risk | L | I | Rating | Mitigation |
| --- | --- | --- | --- | --- | --- |
| O01 | Key person dependency — platform critically exposed to individual founder departure. | 2 | 3 | 6 HIGH | Role documentation from Day 0. IP assignment agreements. Vesting schedule with cliff. Identify and recruit at least one additional technical co-founder before MVP build. |
| O02 | Merchant churn post-lock-in expiry. | 2 | 2 | 4 MEDIUM | Build platform value that exceeds lock-in obligation. Analytics dashboard, promotional tools, and network value should make renewal the default decision. |
| O03 | Negative press / brand incident (e.g., data breach, fraud event). | 1 | 3 | 3 MEDIUM | Incident response plan before launch. Data breach notification procedure (ICO 72-hour requirement). PR / crisis communications protocol. |